## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ankitha BM | 2025-12-04 | CORS issue while accessing backend APIs from frontend | Sprint 1 | Ankitha BM | Configuration | Enabled CORS in backend | 2025-12-05 | Closed | Issue resolved
2 | Yellu Harshitha Reddy | 2025-12-05 | Login API accepts empty credentials | Sprint 1 | Snehalatha Reddy | Validation | Added input validation | 2025-12-06 | Closed | Validation successful
3 | Snehalatha Reddy | 2025-12-06 | User profile data not saved correctly | Sprint 1 | Snehalatha Reddy | Data Handling | Fixed JSON storage logic | 2025-12-06 | Closed | Data persistence verified
4 | Arjun Rankela | 2025-12-06 | Agents not invoked correctly via LangChain | Sprint 2 | Deepak Kumar Hota | Logic Defect | Corrected agent invocation flow | 2025-12-07 | Closed | Agents working as expected
5 | Deepak Kumar Hota | 2025-12-07 | Orchestrator not combining agent outputs properly | Sprint 2 | Deepak Kumar Hota | Integration | Updated orchestration logic | 2025-12-08 | Closed | Unified response generated
6 | Subhash J | 2025-12-07 | Follow-up questions losing previous context | Sprint 3 | Sagar Gowd | Memory Issue | Implemented shared memory | 2025-12-08 | Closed | Context retained
7 | Sagar Gowd | 2025-12-08 | Delay in Groq LLM API response | Sprint 3 | Sagar Gowd | Performance | Added timeout handling | 2025-12-09 | Closed | Performance improved
8 | Palak Mehla | 2025-12-09 | Wellness plan markdown not rendered properly | Sprint 4 | Karthik Bhandarkar | UI Defect | Fixed markdown rendering | 2025-12-10 | Closed | UI rendering fixed
9 | Karthik Bhandarkar | 2025-12-10 | Page refresh causes UI break | Sprint 4 | Karthik Bhandarkar | UI / Routing | Fixed routing logic | 2025-12-11 | Closed | Navigation stable
10 | Komali Priya Mokkapati | 2025-12-10 | Error messages not user-friendly | Sprint 4 | Komali Priya Mokkapati | UX Defect | Improved error messages | 2025-12-11 | Closed | Better user experience
11 | Chhavi | 2025-12-10 | Invalid follow-up input not handled | Sprint 4 | Chhavi | Validation | Added follow-up validation | 2025-12-11 | Closed | Edge case handled
12 | Hemangi Borase | 2025-12-11 | Loading indicator missing during API calls | Sprint 4 | Hemangi Borase | UI Enhancement | Added loading spinner | 2025-12-11 | Closed | UX improvement
13 | Abhilash KR | 2025-12-11 | Backend logs insufficient during failures | Sprint 4 | Abhilash KR | Logging | Improved logging messages | 2025-12-11 | Closed | Easier debugging

## Sheet2
Logical
User Interface
Maintainability
Standards
Others